## WBS Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Status
1.0 | Project Background & Action Plan | Renu (Team Leader) | 2026-02-15 | 2026-02-18 | Completed
2.0 | Dataset Acquisition & Cleaning | Komal (Data Lead) | 2026-02-19 | 2026-02-22 | Completed
3.0 | Exploratory Data Analysis (EDA) | Vanshika (Research) | 2026-02-23 | 2026-03-28 | Completed
4.0 | Baseline Model Development | Preeti (Model Builder) | 2026-03-01 | 2026-03-07 | Completed
5.0 | Model Optimization & Testing | Vanshika & Preeti | 2026-03-08 | 2026-03-13 | Completed
6.0 | Final Report & Documentation | Renu & Komal | 2026-03-14 | 2026-03-17 | Completed
7.0 | Presentation & Project Demo | Priyanka (Presentation) | 2026-03-18 | 2026-03-20 | Completed